## CITY OF NEW LONDON, CONNECTICUT

COMMUNITY DEVELOPMENT BLOCK GRANT PROGRAM

FIFTY FIRST PROGRAM YEAR ACTION PLAN SCHEDULE

JULY 1, 2025 - JUNE 30, 2026

2024

December 6		ODP provides notice to Departments/Boards/Agencies re: Application submissions 				Publish Block Advertisement re: Application Availability

December 17		ODP holds CDBG Application Information Session via ZOOM Meeting @

10:00 a.m.

2025

January 9		Deadline for submission of proposals to ODP

February 3			Publish Notice of First Public Hearing

February 11/13	Citizens Advisory Committee (CAC) reviews proposals and submits program 					recommendations to Administration

CAC meets w/new applicants:  Tuesday, Feb. 11 @ 4:00 p.m. for agency presentations              	              			   Thursday, Feb. 13 @ 4:00 p.m. for recommendations

February 18		First Public Hearing 5:30 p.m.

(Sign in when you arrive at Council Chambers)

March 3		City Council receives recommendations of CAC and Administration

March 17		6:30 p.m.  Council Public Welfare Committee makes funding recommendations to 					     Council based on applications submitted

7:00 p.m.  City Council reviews funding recommendations and establishes provisional 					     funding recommendations

March 19 or 20	Publish summary of proposed Annual Action Plan and Notice of Second Public Hearing

April 7		Second Public Hearing 6:00 p.m.

# April 21 		City Council approves Annual Action Plan and authorizes the Mayor to submit

# to HUD

May 15		City submits Annual Action Plan to HUD

ODP begins preparation of Environmental Review

May 28		City publishes Notice of Request for Release of Funds

June 13		City forwards Request for Release of Funds to HUD

July 1, 2024		PY51 Program Year begins – Subrecipient’s Contracts Executed